## Snagging Log
Projectory UAE Handover Snagging Log
Give every snag one item ID. Keep the original item open until the repair has been tested in the property.
Open items |  | Closed |  | Overdue |  | Due in 7 days
0 |  | 0 |  | 0 |  | 0
Item ID | Room / area | Exact location | Category | Description | Severity | Date found | Photo / video reference | Developer case number | Responsible team | Target date | Access needed | Status | Reinspection date | Closure notes

## Handover Checklist
UAE Off-Plan Handover Checklist
Use this alongside the SPA, handover notice and the developer's official process. The exact documents and sequence vary by contract and emirate.
Completion
0%
Stage | Check | Complete | Evidence / reference | Responsible party | Notes
Before appointment | Read the handover notice against the SPA and addenda | Not started |  | Buyer
Before appointment | Reconcile the statement of account with receipts and bank transfers | Not started |  | Buyer / developer
Before appointment | Notify the mortgage lender if final finance is required | Not started |  | Buyer / lender
Before appointment | Pack the signed floor plan, registration documents and payment evidence | Not started |  | Buyer
Before appointment | Confirm inspector authority and access arrangements | Not started |  | Buyer / developer
At inspection | Complete a first-pass walk-through before recording individual snags | Not started |  | Buyer / inspector
At inspection | Inspect room by room and give every snag one item ID | Not started |  | Buyer / inspector
At inspection | Photograph meter readings and test permitted utilities and controls | Not started |  | Buyer / inspector
At inspection | Record keys, cards, remotes, parking, storage and manuals received | Not started |  | Buyer / developer
At inspection | Obtain the snag-list case number and target repair dates | Not started |  | Developer
At inspection | Confirm who handles defects in common areas | Not started |  | Developer / building management
After keys | Activate electricity, water, cooling and building access | Not started |  | Buyer / service providers
After keys | Test repaired items in the property before accepting closure | Not started |  | Buyer / contractor
After keys | Log issues that appear only after normal use | Not started |  | Buyer
After keys | Confirm service-charge responsibility and building contacts | Not started |  | Buyer / building management
After keys | Store warranties, manuals and emergency contacts | Not started |  | Buyer
After keys | Escalate overdue or recurring defects with a short chronology | Not started |  | Buyer / developer
After keys | Confirm rental or move-in readiness after repairs and administration | Not started |  | Buyer

## Read Me
How to use this workbook
A practical record for UAE off-plan property handover, snagging and aftercare.
Step | Action | How to use it
1 | Inspect and number | Give every issue a unique ID. Describe the exact location, symptom and expected repair. Add a wide photo and a close-up.
2 | Submit and assign | Use the developer's official aftercare system. Enter the case number, responsible team and target date in the Snagging Log.
3 | Re-test before closing | Test the repaired item in the property. If the fault returns, retain the original history and move the status to Recheck.
Severity | Use for | Immediate response
Urgent | Safety issue, active leak, loss of essential service or damage that is worsening | Protect people and property, notify the responsible party immediately, and preserve evidence and receipts.
Material | A defect that prevents normal use, departs materially from the contracted unit or keeps returning | Document clearly, obtain a case number and set an escalation date.
Minor | Cosmetic or small finishing issue that does not prevent normal use | Record it precisely and include it in the agreed repair schedule.
Scope note: This workbook is for practical record-keeping. Contract terms, warranty rights and complaint routes vary by developer and emirate. Seek qualified technical or legal advice for a material, recurring or disputed defect.
Prepared by | Projectory Editorial Team
Version | 18 August 2026
Related guide | https://projectory.ae/insights/uae-off-plan-property-handover-defects-and-aftercare/